## Sheet1
| Start Date | completed | remaining | duration
Brainstorm/finalize aspects of project | 2013-05-29 | 6 | 0 | 6
create general base life form | 2013-06-04 | 0 | 3 | 3
create a generic map | 2013-06-04 | 0 | 4 | 4
create other types of terrain, e.g. water | 2013-06-08 | 0 | 4 | 4
create differentiated life forms, set up predator/prey relationships, gender specific mating, etc | 2013-06-07 | 0 | 5 | 5
create "gangs" within species; in-group, out-group | 2013-06-12 | 0 | 2 | 2
create vegetation, where to find base producers | 2013-06-12 | 0 | 2 | 2
incorporate memory for life forms; where food was last found | 2013-06-14 | 0 | 3 | 3
incorporate weather | 2013-06-14 | 0 | 2 | 2
Formulas:
Start Date = [Start Date, row above]+[duration, row above]